MedAI Paper 1

Full Study Protocol, Experiment Plan & Manuscript Blueprint

From Prompting to Fine-Tuning: Evidence-Grounded Epilepsy Phenotyping Across Heterogeneous Clinical Documents with Local Medical Language Models

MRI reports • EEG reports • Progress notes • Epilepsy/condition notes • EMU/presurgical notes • Conference/procedure documentation

Updated study design | September 2026

# 1. Executive Study Specification

| Element | Paper 1 specification |
| --- | --- |
| Study type | Retrospective clinical NLP / information extraction validation study. |
| Primary question | Can a locally deployed medical LLM reliably extract structured, evidence-grounded epilepsy phenotypes across heterogeneous clinical document types, and what degree of prompting/constraint/fine-tuning is required? |
| Core novelty target | Controlled comparison of traditional NLP, zero-shot, few-shot, schema constraints, evidence grounding and PEFT across multiple epilepsy document families. |
| Inputs | TEXT ONLY: MRI reports, EEG reports, progress/condition notes, EMU/presurgical/conference/procedure documentation as available. |
| Not in Paper 1 | Raw MRI voxels/DICOM/NIfTI and raw EEG waveforms. Those enter Paper 2. |
| Output | Modular structured epilepsy phenotype + field-level source evidence + document/date provenance. |
| Gold standard | Expert clinician annotation with adjudication and inter-rater agreement. |
| Unit of split | Patient, never individual note. |
| Intended use | Research phenotyping / data structuring; not autonomous diagnosis or treatment recommendation. |

# 2. Why This Paper Matters

• Epilepsy information is distributed across heterogeneous documents rather than one note type.

• MRI reports contain structural interpretations; EEG reports contain electrophysiologic interpretations; progress and specialty notes contain semiology, disease course and treatment history.

• A system that works on only progress notes may not generalize to the actual epilepsy record.

• Evidence grounding is essential because a structured field should be auditable back to the source statement.

• Fine-tuning should be evaluated against prompting rather than assumed necessary.

• The study creates the validated text phenotype layer needed by later MedAI multimodal papers.

# 3. Research Questions and Hypotheses

| RQ | Question | Hypothesis to test |
| --- | --- | --- |
| RQ1 | How well does Med42 perform zero-shot across heterogeneous epilepsy documents? | Establish baseline; no assumed superiority. |
| RQ2 | Does few-shot prompting improve extraction? | H1: improvement for at least some phenotype/document classes. |
| RQ3 | Do schema constraints improve reliability? | H2: higher schema-valid output rate and fewer format failures. |
| RQ4 | Does evidence grounding reduce unsupported extraction? | H3: lower unsupported-claim rate and higher auditability. |
| RQ5 | Does PEFT improve task performance? | H4: benefit increases with sufficient expert-labeled data. |
| RQ6 | How much labeled data is needed? | H5: learning curves reveal the annotation/performance tradeoff. |
| RQ7 | Does performance differ by document type? | H6: extraction difficulty varies across MRI, EEG, progress, EMU/presurgical and other documents. |
| RQ8 | Does a medical LLM outperform conventional or general-language alternatives? | Optional comparative hypothesis; test rather than presume. |

# 4. Document Taxonomy and Sampling

| Document family | Examples | Primary information |
| --- | --- | --- |
| MRI | Radiology report; epilepsy MRI report | normal/abnormal, HS, FCD, lesion type, location, laterality, MRI-negative statement |
| EEG | Routine EEG; ambulatory EEG; EMU/video-EEG interpretation | IEDs, seizures captured, ictal onset, background, localization/laterality |
| Progress | Neurology/epilepsy follow-up | seizure frequency, semiology, medication use/response, current status |
| Condition/specialty | Initial epilepsy consult; presurgical evaluation | diagnosis, onset, semiology, drug resistance, localization hypothesis |
| EMU/discharge | EMU admission/discharge summary | captured events, EEG conclusion, diagnosis, medication changes |
| Conference | Epilepsy surgery conference | multidisciplinary localization, concordance, recommendation |
| Procedure | SEEG, resection, neurostimulation documentation if included | procedure, target, laterality, intervention |

• Create a pre-annotation inventory: patients, notes, notes/patient, document types, years, length distributions, duplicates/templates and missingness.

• Define whether every patient needs all document types; likely not. Sampling should preserve real heterogeneity while ensuring enough examples per major document class for stratified evaluation.

• Consider a deliberately balanced development sample for annotation-manual refinement, but preserve a defensible natural distribution in the locked test set.

• Document selection rules must be deterministic and written before final evaluation.

# 5. Modular Phenotype Ontology

Use modules so fields are only evaluated where they are clinically meaningful. Avoid forcing MRI fields onto progress notes or EEG fields onto MRI reports.

| Module | Candidate fields | Notes |
| --- | --- | --- |
| Clinical/seizure | epilepsy/seizure type; awareness; semiology; age at onset; frequency; duration/status history | Explicit/uncertain/historical distinctions required. |
| Medication/treatment | current ASMs; prior ASMs; failures; adverse effects; drug resistance; surgery/neurostimulation history | Medication status is temporally sensitive. |
| Clinical localization | left/right/bilateral/unknown; temporal/frontal/parietal/occipital/multifocal | Separate clinician hypothesis from confirmed localization. |
| EEG report | study type; IED presence; IED localization/laterality; seizures captured; ictal onset; background | Keep interictal and ictal evidence separate. |
| MRI report | normal/abnormal; HS; FCD; lesion/etiology; location/laterality; MRI-negative designation | Distinguish suspected vs definite findings. |
| Integrated textual phenotype | clinical vs EEG vs MRI localization; agreement/discordance descriptors if explicitly documented | Do not infer multimodal concordance unless defined as a separate derived rule. |
| Provenance | source document ID/type/date; evidence span; certainty; temporal status | Required for auditability. |

# 6. Field Specification Template

| For every field define | Example |
| --- | --- |
| Name | ictal_onset_laterality |
| Clinical definition | Laterality of documented ictal EEG onset. |
| Allowed values | left / right / bilateral / diffuse / unknown / not_documented |
| Source types | EEG/EMU reports primarily. |
| Evidence rule | Minimal sufficient text span supporting value. |
| Negation rule | Do not convert 'no clear lateralization' to a side. |
| Uncertainty rule | Possible/suggestive ≠ confirmed; encode certainty. |
| Temporal rule | Attach study/report date. |
| Conflict rule | Preserve conflicting observations rather than silently overwrite. |
| Normalization rule | Map synonymous language to canonical enum. |
| Evaluation rule | Exact categorical match plus evidence correctness. |

# 7. Annotation Study

## 7.1 Annotator roles

• At least one epilepsy-domain clinician/expert should own definitions and adjudication.

• Use two independent annotators on a meaningful subset; ideally clinicians or trained annotators with specialist oversight.

• Keep an adjudication log explaining recurring disagreements.

## 7.2 Annotation manual

• Definitions, allowed values, examples/non-examples.

• Negation, uncertainty, historical/current status, hypothetical/planned statements.

• Copied-forward statements and contradictory documentation.

• Evidence-span rules and minimal sufficient evidence.

• Multi-valued fields and repeated events.

• Not documented vs unknown vs not applicable.

• Document-specific rules for MRI and EEG terminology.

• Adjudication workflow and version history.

## 7.3 Pilot

• Select a heterogeneous pilot spanning all major document families, long/short notes and common/rare phenotypes.

• Independently annotate; calculate agreement; discuss disagreements.

• Revise ontology/manual before scaling.

• Freeze the production annotation version before creating the final gold test set.

## 7.4 Gold-standard deliverables

• Annotated structured labels

• Evidence spans

• Document metadata

• Annotator IDs

• Adjudication status

• Ontology/manual version

• Agreement report

# 8. Cohort Splitting and Leakage Prevention

| Partition | Use |
| --- | --- |
| Training | PEFT and supervised baseline training; source pool for few-shot examples. |
| Validation/development | Prompt design, example strategy, hyperparameters, parser/schema debugging. |
| Locked test | Final comparison only; no prompt/model changes after inspection. |
| Optional temporal/external | Generalization evaluation only. |

• Split by patient. Every MRI report, EEG report and clinical note belonging to one patient stays in one partition.

• Detect exact/near-duplicate notes and copied-forward text.

• Few-shot examples cannot come from test patients.

• Fine-tuning cannot use test or external patients.

• Do not select prompts based on final test performance.

• Preserve document-type distributions and report them per split.

# 9. Experimental Arms

| ID | System | What it isolates |
| --- | --- | --- |
| B0 | Rules/regex/dictionary baseline | Transparent deterministic extraction. |
| B1 | Supervised clinical NLP/BioClinicalBERT-style baseline | Conventional learned clinical NLP. |
| M0 | Med42 zero-shot | Base instruction-following capability. |
| M1 | Med42 few-shot | In-context demonstration effect. |
| M2 | M1 + schema-constrained output | Structured generation effect. |
| M3 | M2 + evidence grounding | Evidence requirement effect. |
| M4 | Med42 PEFT | Task-specific adaptation effect. |
| M5 | M4 + schema constraints | Structured fine-tuned system. |
| M6 | M5 + evidence grounding | Full MedAI Paper-1 system. |
| C1 optional | General open LLM under comparable prompting | Medical-specialization control. |
| C2 optional | Second medical LLM | Model-family robustness. |

# 10. Prompt Design

• Role: clinical information extraction assistant; explicitly not asked to diagnose.

• Instruction: extract only information supported by the provided document/context.

• Unknown/not documented must be allowed and preferred over guessing.

• Use the exact versioned schema and canonical enums.

• Few-shot demonstrations should represent heterogeneous documents but remain fixed for final evaluation.

• Specify evidence output for every non-null field.

• Use deterministic/low-temperature decoding and document all generation settings.

• Predefine long-document strategy: section-aware chunking, retrieval or hierarchical extraction.

• Store raw response before parsing/repair.

# 11. Schema-Constrained Output and Validation

• Implement JSON Schema and/or Pydantic models.

• Validate types, required keys, enumerated values and nested evidence objects.

• Record raw validity, repaired validity and repair method separately.

• Never count a silently repaired value as if the model originally emitted a valid output.

• Version schema changes; final test uses one frozen schema.

• Use document-specific applicable-field masks to avoid penalizing systems for irrelevant fields.

# 12. Evidence Grounding

Recommended output object for each extracted fact: value + certainty + temporal status + evidence text + source document/date. Character offsets may be added if robust.

• Evaluate whether evidence actually supports the extracted value.

• Measure evidence recall/coverage: did the model provide support for claims that should have evidence?

• Measure unsupported claim rate independently from ordinary classification error.

• Distinguish correct value/wrong evidence from wrong value/correctly copied text.

• Where notes conflict, preserve multiple dated claims or apply a prespecified aggregation rule.

# 13. Fine-Tuning / PEFT

• Use LoRA/QLoRA first unless full fine-tuning has a justified scientific reason.

• Training target should mirror final schema and evidence structure.

• Train only on high-quality adjudicated labels for the primary experiment.

• Record base checkpoint/hash, adapter rank/alpha/dropout, quantization, optimizer, LR, batch/accumulation, epochs, seed, hardware and checkpoint rule.

• Keep the inference contract identical enough that prompted and fine-tuned systems can be compared fairly.

## 13.1 Learning-curve design

• Use increasing training sizes such as 25, 50, 100, 250, 500+ examples/patients as feasible after the pilot.

• Prefer repeated subsamples at each size if compute permits.

• Track overall F1, document-type F1, evidence correctness and unsupported claims versus annotation size.

• Record annotation time so performance can be related to human labeling cost.

• The scientific result is the curve; do not assume fine-tuning must win.

# 14. Long Document and Multi-Document Handling

• For Paper 1, decide whether the atomic inference input is one document or a predefined bundle of documents. A clean first design is document-level extraction followed by deterministic patient-level aggregation.

• Document-level evaluation is easier to audit; patient-level aggregation can be a secondary experiment.

• Long documents: preserve section headers and use section-aware chunking rather than arbitrary token cuts.

• Patient-level aggregation must define conflict resolution, recency, duplicate evidence and multiple-event handling.

• Do not let patient-level aggregation leak future documentation into a temporally scoped field.

# 15. Evaluation Metrics

| Category | Metrics |
| --- | --- |
| Extraction | Per-field precision, recall, F1, support; macro/micro summaries where appropriate. |
| Categorical reliability | Accuracy/balanced accuracy/specificity when meaningful. |
| Schema | Raw valid-output rate, parse failures, repair rate. |
| Grounding | Evidence precision/correctness, evidence recall/coverage. |
| Unsupported output | Unsupported-claim/hallucination rate. |
| Language phenomena | Negation, uncertainty, temporality and conflict errors. |
| Document heterogeneity | Metrics separately for MRI, EEG, progress, specialty/EMU/presurgical and other predefined classes. |
| Efficiency | Latency, throughput, GPU memory, token usage. |
| Annotation | Inter-rater agreement, adjudication rate, annotation time. |

# 16. Primary Endpoint and Statistical Analysis

• Predeclare one primary model-performance endpoint, e.g., macro F1 across a frozen set of core phenotype fields.

• Key secondary endpoints: unsupported-claim rate, evidence correctness and schema validity.

• Use patient-level bootstrap confidence intervals where suitable to respect clustered documents.

• Use paired comparisons because systems are evaluated on the same held-out patients/documents.

• Control multiple formal comparisons or label broad pairwise analyses exploratory.

• Report absolute differences and confidence intervals, not p-values alone.

• Predefine handling for rare/undefined metrics.

• Document-type interaction/stratification should be planned before final evaluation.

# 17. Sample Size and Annotation Budget

• Run the pilot first to estimate phenotype prevalence, document-type distribution and minutes per annotation.

• Ensure the locked test set has enough positive examples for the primary fields and enough documents in each major class to support stratified estimates.

• Rare phenotypes can be enriched in training, but test prevalence must be transparently described.

• Use precision/CI targets and positive-case counts rather than an arbitrary total note count.

• PEFT development data requirements may exceed those needed merely to estimate test performance; plan these separately.

# 18. Error Taxonomy

| Error | Definition |
| --- | --- |
| Missed fact | Supported phenotype not extracted. |
| Wrong label | Evidence found but normalized incorrectly. |
| Negation | Negated finding extracted as present. |
| Uncertainty | Possible/suspected converted to definite. |
| Temporal | Historical/current/planned state confused. |
| Medication status | Prior/current/failed medication confused. |
| EEG semantic | Interictal vs ictal or localization semantics confused. |
| MRI semantic | Lesion/HS/FCD/laterality interpretation wrong. |
| Conflict | Contradictory notes/reports handled incorrectly. |
| Unsupported inference | Claim absent from source evidence. |
| Evidence mismatch | Value may be correct but cited text does not support it. |
| Schema | Invalid/missing/wrongly typed structured output. |

# 19. Robustness and Generalization

• By document type.

• By note/report length.

• By note template/era where applicable.

• By common versus rare phenotype.

• By clinician/service if permissible and sufficiently powered.

• Temporal holdout if records span multiple eras.

• External site validation if accessible.

• Optional second model family to test model dependence.

• Prompt perturbation should be limited and prespecified, not an unbounded prompt-search exercise.

# 20. Reproducibility Requirements

| Artifact | Must contain |
| --- | --- |
| Repository | Ingestion, preprocessing, prompts, schemas, inference, parsing, evaluation, statistics. |
| Prompt registry | Exact text, version, few-shot IDs, rationale/change history. |
| Schema registry | Versioned JSON/Pydantic definitions. |
| Model registry | Checkpoint, hash, quantization, adapters. |
| Run manifest | Code/model/prompt/schema version, input IDs, decoding, seed, hardware, timestamps. |
| Container | Docker/Apptainer as appropriate for approved environment. |
| Evaluation harness | Locked reproducible final evaluation. |
| Audit output | Raw response, parsed response, validity, evidence, repairs, errors. |
| Data dictionary | Document types, phenotype fields, provenance, missingness. |

# 21. Governance, Privacy and Intended Use

• Obtain appropriate IRB determination/approval and data-use permissions.

• Use institutionally approved secure local compute for PHI.

• Do not transmit PHI to external APIs/services without explicit approval.

• Define de-identification for manuscript examples and any shared artifact.

• Maintain minimum-necessary access and auditability.

• Paper language should say research phenotyping/information extraction; avoid unsupported clinical deployment, diagnosis or treatment claims.

# 22. Full Manuscript Blueprint

## 22.1 Abstract

• Background

• Objective

• Cohort/document families

• Annotation/gold standard

• Systems compared

• Primary metrics

• Main results

• Conclusion/intended use

## 22.2 Introduction

• Epilepsy phenotype information is distributed across heterogeneous documentation.

• Structured research variables are costly to curate manually.

• Clinical LLMs offer flexible extraction but require validation for reliability and evidence support.

• Gap: controlled study of prompting → constraints → grounding → PEFT across MRI/EEG/clinical document families.

• End with explicit contributions and research questions.

## 22.3 Related Work

• Clinical information extraction/phenotyping

• Clinical BERT/NER

• Zero/few-shot clinical LLM extraction

• Medical LLMs/Med42

• Constrained structured generation

• Evidence grounding/factuality

• PEFT/LoRA/QLoRA

• Epilepsy NLP/cohort identification

## 22.4 Methods

• Study setting/governance

• Cohort/document selection

• Document taxonomy

• Phenotype ontology

• Annotation/gold standard

• Patient splits/leakage control

• Baselines

• Prompting

• Schema constraints

• Evidence grounding

• PEFT/learning curve

• Long-document/aggregation strategy

• Metrics

• Statistics

• Implementation/hardware

## 22.5 Results

• Cohort and document characteristics

• Phenotype prevalence

• Annotation agreement

• Primary model table

• Per-field results

• Document-type stratification

• M0→M6 ablation

• Learning curves

• Evidence/hallucination

• Schema validity

• Efficiency

• Error analysis

• Generalization

## 22.6 Discussion

• Answer each RQ explicitly.

• Interpret which adaptation steps actually mattered.

• Discuss fine-tuning benefit relative to annotation cost.

• Discuss document-type differences.

• Clinical research utility and human review.

• Comparison with prior work.

• Generalizability and failure modes.

• Explain how Paper 1 enables later raw EEG/MRI multimodal MedAI studies.

## 22.7 Limitations

• Retrospective design

• Single-site if applicable

• Rare labels

• Documentation bias

• Annotator subjectivity

• Model/version dependence

• Copy-forward/template contamination

• No prospective clinical-impact claim

• Data-sharing limitations

## 22.8 Conclusion

One evidence-limited conclusion about reliable structured epilepsy phenotyping across heterogeneous clinical documents and the observed value of prompting, grounding and/or fine-tuning.

# 23. Required Figures and Tables

| Artifact | Content |
| --- | --- |
| Figure 1 | Cohort/document flow and patient-level partitions. |
| Figure 2 | Paper-1 architecture: heterogeneous documents → LLM → schema validation → evidence-grounded modular phenotype. |
| Figure 3 | Experimental ladder B0/B1 and M0→M6. |
| Figure 4 | PEFT learning curves vs annotation volume. |
| Figure 5 optional | Error/evidence-grounding results by document type. |
| Table 1 | Patient and document characteristics. |
| Table 2 | Phenotype ontology, prevalence and annotation agreement. |
| Table 3 | Primary system comparison. |
| Table 4 | Per-document-type performance. |
| Table 5 | Evidence, unsupported claims, schema validity and efficiency. |
| Supplement | Full prompts, schema, annotation rules, hyperparameters, per-field results, statistics and additional errors. |

# 24. Submission-Ready Artifact Checklist

• IRB/governance documentation and cohort specification.

• Frozen patient split manifest.

• Document taxonomy and sampling rules.

• Phenotype ontology/schema.

• Annotation manual and adjudication log.

• Gold labels + evidence annotations.

• Agreement analysis.

• Rules/BERT baselines.

• Med42 M0–M6 configs.

• PEFT adapters/configs and learning-curve outputs.

• Raw and parsed held-out predictions.

• Evidence/hallucination evaluation.

• Statistical scripts and confidence intervals.

• Error-review dataset.

• Reproducible figures/tables.

• Code/container release plan consistent with policy.

• Manuscript + supplement + reporting checklist.

# 25. Stage-Gated Execution Plan

| Gate | Tasks | Exit criterion |
| --- | --- | --- |
| G0 | IRB/governance + full document inventory | Approved path and feasible source data. |
| G1 | Ontology/schema v0.1 | Expert-approved candidate fields. |
| G2 | Heterogeneous pilot annotation | Manual refined; agreement issues understood. |
| G3 | Freeze annotation protocol | Schema/manual v1.0. |
| G4 | Scale annotation + adjudication | Gold train/val/test complete. |
| G5 | Traditional + zero/few-shot baselines | Reproducible baseline results. |
| G6 | Schema + evidence systems | M2/M3 validated. |
| G7 | PEFT + learning curves | M4–M6 frozen. |
| G8 | Freeze test protocol | No further test-driven development. |
| G9 | Final held-out evaluation | Primary/secondary metrics + CIs. |
| G10 | Clinical error review | Final taxonomy and case review. |
| G11 | Manuscript/supplement | Coauthor-reviewed submission package. |

# 26. Minimum, Strong and Flagship Versions

| Level | Required scope |
| --- | --- |
| Minimum | MRI + EEG + progress/specialty text represented; clinician gold standard; rules/BERT; Med42 zero/few-shot; schema; patient-level held-out test; document-stratified evaluation. |
| Strong | Minimum + evidence grounding + PEFT + learning curve + double annotation + unsupported-claim evaluation + reproducibility container. |
| Flagship | Strong + second LLM family + temporal/external validation + robust provenance/evidence evaluation + shareable evaluation artifacts where governance permits. |

# 27. Immediate Next Steps

• Inventory counts of MRI reports, EEG reports, progress notes, epilepsy/condition notes, EMU/presurgical/conference/procedure notes by patient.

• Choose the initial modular phenotype fields and identify which document families can support each.

• Draft annotation manual v0.1 with explicit MRI/EEG terminology rules.

• Select a heterogeneous pilot set before any large annotation effort.

• Identify annotators/adjudicator.

• Create patient-level split policy and duplicate/copy-forward detection.

• Implement versioned JSON/Pydantic schema.

• Establish local Med42 inference and run logging.

• Implement M0/M1 on pilot data before PEFT.

• Use pilot prevalence and annotation time to determine final annotation budget and test-set size.

# 28. Definition of Done

Paper 1 is complete when a clinician-adjudicated, patient-level held-out corpus spanning the prespecified heterogeneous epilepsy document families has been evaluated with traditional NLP, Med42 zero-shot/few-shot, schema-constrained, evidence-grounded and PEFT-adapted systems; the incremental value of each component is quantified with confidence intervals; performance is stratified by document type; evidence correctness and unsupported claims are measured; annotation reliability and fine-tuning learning curves are reported; errors receive clinical review; the full pipeline is versioned and reproducible; and the manuscript limits its claim to evidence-grounded structured epilepsy phenotyping from clinical documentation for research use.